## Sheet1
Product Backog Team 50 CS 2340
Work Items | Initial Estimate | Adjust Factor | Adjust Estimate | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
Setup version control | 4 | 0.3 | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Home screen | 3 | 0.4 | 4.2 | 4.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Login | 10 | 0.4 | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Registration | 10 | 0.4 | 14 | 14 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Integrate database | 6 | 0.4 | 8.4 | 8.4 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0
UI design | 12 | 0.4 | 16.8 | 16.8 | 10 | 7 | 0 | 12 | 0 | 8 | 0 | 0
Profile Page | 8 | 0.3 | 10.4 | 10.4 | 10.4 | 10.4 | 0 | 0 | 0 | 0 | 0 | 0
Ability to add info | 2 | 0.3 | 2.6 | 2.6 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0
Ability to edit info | 2 | 0.3 | 2.6 | 2.6 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0
Logout functionality | 2 | 0.3 | 2.6 | 2.6 | 2.6 | 2.6 | 0 | 0 | 0 | 0 | 0 | 0
Store profile info in database | 4 | 0.3 | 5.2 | 5.2 | 5.2 | 5.2 | 4 | 0 | 0 | 0 | 0 | 0
Search Page available on Profile | 3 | 0.3 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 0 | 0 | 0 | 0 | 0
Implement Recycler views | 12 | 0.3 | 15.6 | 15.6 | 15.6 | 15.6 | 15.6 | 2 | 0 | 0 | 0 | 0
Hook up app to Rotten Tomatoes | 8 | 0.3 | 10.4 | 10.4 | 10.4 | 10.4 | 10.4 | 0 | 0 | 0 | 0 | 0
Search latest DVDs | 2 | 0.3 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 0 | 0 | 0 | 0
Search Highest Rated movies | 2 | 0.3 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 0 | 0 | 0 | 0
Rating Screen | 4 | 0.3 | 5.2 | 5.2 | 5.2 | 5.2 | 5.2 | 5.2 | 0 | 0 | 0 | 0
Ability to rate and review | 4 | 0.3 | 5.2 | 5.2 | 5.2 | 5.2 | 5.2 | 5.2 | 0 | 0 | 0 | 0
Store ratings on database | 4 | 0.3 | 5.2 | 5.2 | 5.2 | 5.2 | 5.2 | 5.2 | 3 | 0 | 0 | 0
Integrate ratings into movie search | 4 | 0.3 | 5.2 | 5.2 | 5.2 | 5.2 | 5.2 | 5.2 | 4 | 0 | 0 | 0
View rated movies | 5 | 0.3 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 0 | 0 | 0
Ability to get recommendations based on major | 3 | 0.3 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 0 | 0 | 0
Ability to get recommendations based on overall ratings | 3 | 0.3 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 0 | 0 | 0
Ability to ban/lock users | 6 | 0.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 8.4 | 0 | 0
Admin Features | 6 | 0.3 | 7.8 | 7.8 | 7.8 | 7.8 | 7.8 | 7.8 | 7.8 | 7.8 | 0 | 0
Ability to get recommendations based on genre | 3 | 0.3 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 3.9 | 0 | 0
Testing | 20 | 0.4 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 0
Total | 148 |  | 204.3 | 199.1 | 165.7 | 155.7 | 122.3 | 102.4 | 69.4 | 56.1 | 28 | 0

## Sheet2
Set up version control
Tasks | Resonsible | Status | 1 | 2 | 3
Setup project Github Page | Neil | Completed | 2 | 1 | 0
Install Android Studio | All | Completed | 2 | 1 | 0
Write gradle files | All | Completed | 3 | 1 | 0
Total |  |  | 7 | 3 | 0

## Sheet3
M3 - Login/Logout
Tasks | Resonsible | Status | 1 | 2 | 3
Design Welcome screen | Forester | Completed | 2 | 1 | 0
Login Functionality | Tommy | Completed | 2 | 1 | 0
Registration Functionality | Forester | Completed | 3 | 1 | 0
Models for MVC | Neil | Completed | 7 | 3 | 0
Setup database; integrate user info | Scott | Completed | 8 | 4 | 0
10 Use cases | Neil | Completed | 1 | 0 | 0
Context Diagram | Neil | Completed | 2 | 0 | 0
Set up singleton userManager | Tommy | Completed | 3 | 1 | 0
Total |  |  | 28 | 11 | 0

## Sheet4
M4 - Registration
Tasks | Resonsible | Status | 1 | 2 | 3 | 4
UML Domain Model | Neil, Tommy | Completed | 5 | 0 | 0 | 0
Brainstorrm candidate classes | Neil, Tommy | Completed | 2 | 0 | 0 | 0
User Registration database integration | Scott | Completed | 4 | 2 | 0 | 0
Add cancel button for registration | Forester | Completed | 1 | 0 | 0 | 0
Touch up on registration UI | Tommy | Completed | 4 | 4 | 1 | 0
Profile Page | Neil | Completed | 4 | 1 | 0 | 0
Edit Profile | Neil | Completed | 2 | 2 | 0 | 0
Store user info in database | Scott | Completed | 5 | 3 | 1 | 0
Total |  |  | 27 | 12 | 2 | 0

## Sheet5
M5 - Movie Search
Tasks | Resonsible | Status | 1 | 2 | 3
Learn REST | All | Completed | 4 | 0 | 0
Learn Volley for Android | All | Completed | 4 | 0 | 0
Async tasks that makes calls to RT for searching movies | Neil, Tommy | Completed | 4 | 6 | 0
Design Search page | Scott | Completed | 4 | 2 | 0
Implement Recycler views | Forester | Completed | 10 | 4 | 0
Integrate images into movie list | Forester | Completed | 2 | 0 | 0
Improve UI for search page | Scott | Completed | 2 | 0 | 0
Set up movie manager singleton class | Neil | Completed | 3 | 3 | 0
Total |  |  | 33 | 15 | 0

## Sheet6
M6 - Movie Ratings
Tasks | Resonsible | Status | 1 | 2 | 3
Package Diagram | Neil, Scott | Completed | 3 | 0 | 0
Methods to rate movie | Tommy | Completed | 4 | 2 | 0
UI for rating a movie | Forester | Completed | 4 | 2 | 0
Display ratings for each movie | Forester | Completed | 6 | 4 | 0
Store ratings in database | Scott | Completed | 3 | 0 | 0
Adapt movie manager singleton to fit rating purpose | Tommy | Completed | 1 | 0 | 0
Adapt movie object to fit ratings and other movie properties | Tommy | Completed | 1 | 0 | 0
Total |  |  | 22 | 8 | 0

## Sheet7
M7 - Movie Recommendations
Tasks | Resonsible | Status | 1 | 2 | 3
UML Class Diagram | Scott | Completed | 2 | 0 | 0
Set up recommendation button in homepage | Neil | Completed | 1 | 0 | 0
Method to obtain movie ratings based on major | Tommy | Completed | 4 | 1 | 0
Method to obtain movie ratings based on genre | Tommy | Completed | 4 | 2 | 0
Recycler views for movie recommendations | Forester | Completed | 6 | 4 | 0
UI for getting recommendations | Neil | Completed | 3 | 0 | 0
Method to pull information from database | Scott | Completed | 2 | 0 | 0
Total |  |  | 22 | 7 | 0

## Sheet8
M8 - Admin Features
Tasks | Resonsible | Status | 1 | 2 | 3
UML Sequence diagram | Neil, Tommy | Completed | 3 | 0 | 0
Set up admin object | Tommy | Completed | 2 | 0 | 0
Create admin profile | Forester | Completed | 3 | 1 | 0
Adapt login for admin | Scott | Completed | 3 | 0 | 0
Method to obtain users | Forester | Completed | 3 | 2 | 0
Method to lock/ban users | Neil | Completed | 3 | 2 | 0
Recycler views for user list | Neil, Forester | Completed | 6 | 4 | 0
Admin UI | Neil | Completed | 3 | 1 | 0
Total |  |  | 26 | 10 | 0

## Sheet9
M9 - Persistence
Tasks | Resonsible | Status | 1 | 2 | 3
Rejig database schema | Scott | Completed | 6 | 3 | 0
Testing ratings in database | Scott | Completed | 3 | 1 | 0
Testing profile info in database | Tommy | Completed | 3 | 1 | 0
Testing registration info in database | Forester | Completed | 3 | 1 | 0
Testing admin activity in database | Neil | Completed | 3 | 1 | 0
Total |  |  | 18 | 7 | 0

## Sheet10
M10 - Testng and Coding Standards
Task | Resonsible | Status | 1 | 2 | 3
Test PMD, Checkstyle and Lint on listview | Tommy | Completed | 6 | 3 | 0
Test PMD, Checkstyle and Lint on activities | Neil | Completed | 8 | 3 | 0
Test PMD, Checkstyle and Lint on models | Forester | Completed | 2 | 2 | 0
Test PMD, Checkstyle and Lint on database | Scott | Completed | 4 | 2 | 0
Total |  |  | 20 | 10 | 0